## Slide 1: Progress report
Paul Talbot
September 2015

## Slide 2: Path to Degree
Coursework
  Completion of necessary classwork hours
Qualifying Exams
  Four-exam testing based on coursework
Proposal
  Preliminary demonstration of research
Defense
  Final demonstration of achievement
✓
✓
O

## Slide 3: Proposal Development
Determine Work
Implement Methodology
Collect Results
Implement Stochastic Collocation for generalized Polynomial Chaos in RAVEN
Isotropic, Anisotropic, HDMR, Adaptive Anisotropic, Adaptive HDMR
Tensor
Isotropic
Anisotropic
HDMR
Adaptive Anisotropic
Adaptive HDMR
✓
✓
✓
✓
✓
O
Analytic Cases
Multigroup Diffusion
Engineering Code
✓
✓
O
Proposal

## Slide 4: Outstanding Hurdles
BISON test case
    Chosen because of similarity to literature
  Costly solves
    Requires parallelization, time and resources
  Non-deterministic when parallelized
    Decomposing mesh results in slightly different convergence
  Reference case is near to algorithm failing regions
    Slightly different convergence can mean algorithm failure
Result: Many sparse grids have failed to be constructed

## Slide 5: Possible Solutions
Improve existing BISON case
  Find better parameter space to run
  Work with BISON developers to debug convergence failures
Change BISON case
  Find a similar case with more stability
  Work with BISON developers to find “safe” parameter space
Simplify case, move to multiphysics
  Couple BISON and RATTLESNAKE cases
  Neutronics and Fuel Performance
  Work with developers to find appropriate coupled case

## Slide 6: Possible Solutions - Considered
Improve existing BISON case
  Nothing particularly special about this case
  Key developer for case no longer at INL
Change BISON case
  Involves time searching for appropriate case
  Need match between literature and existing BISON cases
Simplify case, move to multiphysics
  Work dependent on dimension reduction with a lab collaborator
  Shifts focus from complexity of one model to nonlinear multiphysics